RICH1 Phone Meeting, 17th August 2007

Present

CERN: Jon Imong

Bristol: Richard Head

Imperial: Bill Cameron, Trevor Savidge, Richard Plackett

Oxford: Neville Harnew, Rohan Senanayake, Brian Ottewell.

Gas Enclosure

There has been essentially no change to the gas enclosure since the last meeting.

There is some concern that the dry air supply is introducing dust which is settling on the mirrors. This needs further investigation.

Richard Head has shipped the dowty seals to CERN yesterday with DHL.      They should arrive with Jon or Fabio soon.

There has been no action by Richard Plackett on the temperature sensors in the gas enclosure, they will be finalised in the first week in September.

Magnet Tests

Rolf has confirmed that the magnet tests will occur in the first two weeks of October.

This means the GE doors and magnetic shield doors will want to go on in the last 10 days of September.

This means we will be limited to access to the GE in the first two weeks in September.

This could be even less as it is probable that the magnetic doors will not the last things in LHCb that have to be installed before the magnet tests can go ahead.

We are waiting to see a full plan/schedule from Rolf for the tests.

Mirrors

The misalignment of the flat mirrors is very minor and can be easily corrected.

The upper flat mirror is off by 1.3mrad

The lower flat mirror is off by 3.2mrad

These require a 1~2mm adjustment on their adjustment screws.

The Spherical rail top fixing needs to be adjusted 5.5 mm to correct the centre of curvature and the whole bottom rail needs to be shimmed to raise it 1mm. The required shims are available at CERN.

The involvement of the surveyors will be important so they must be given plenty of notice for this operation.

We should be able to do this in the first week of September.

HPD Assembly

No change in the plan for dressing the remaining two spare columns during September.

Upper Installation Rails

Last week (6th-10th August) a test installation of the upper HPD rails, the upper chariot and two HPD columns was undertaken.

The rails and chariot arrived at IP8 on Monday in the Oxford van.

The parts were transported underground on Tuesday and some minor alterations were made.

The external rails were mounted on the shield on Wednesday.    The mounting was relatively smooth, however some problems were found.

The lifting lugs were not in the optimal position making it hard to hold the rails straight to install it.

There was also interference between the turnbuckle and the wheels of the chariot.

After this the chariot was installed.    The main problem encountered here was the limited access of the crane due to the TT support bracket that meant the HPD box couldn't be lifted round the rails to put it on them.    To get around this the rails were partially dismounted and the box lifted between them, held suspended on the crane as the rails were reassembled under it, and then the box was lowered onto them.

So far this is the only workable installation procedure we have and it

is not ideal from a safety point of view as it involves people working under a heavy object held on a crane.

Once the chariot was installed on the rails and rolled into the shield it moved very smoothly indeed.

Measurements were made and found to agree with the CAD model to ~1-2mm.

The chariot was removed from the rails in the same way as it was mounted.

The rails were test loaded with 500kg with the support cables off and the deflection was ~twice that predicted in the FEA model.

The rails were dismounted and the cross members sent back to Oxford for adjustment.

The chariot was sent back to IC to be completed.

While the rails were being test loaded the chariot had 2 fully populated HPD columns mounted within it.    This was done using the hall crane in 153 next to the SSB lab. The columns installed very smoothly.    The columns were close packed and one was in an extreme edge position.

Rohan is going to provide design solutions to the clashes between the rail cross-member and the plinth of the chariot.

We would prefer if the adaptations were to extend the cross members rather than to make a cut-out so the PF can pass if necessary.

TS to send Rohan a model of the PF.

The adaptations will be possible for the timescale of a final installation after the magnet tests in October.

Minor changes to the design will probably not require re-certification by CERN.

We still need to locate a suitable spreader beam for craning the box.

We will need to negotiate with the TT to see if their beam can be moved, otherwise the installation will be as with the trials.

Lower Rails

Only a few design details remain to be completed. e.g. mounting points for column extraction frame.

One aspect that needs to be discussed is the securing of the box to the frame.

Brian will come to IC to go through the final design with TS next week.

The CAD model now includes the space limitations in the working area.

Cabling

There has been no change in the cabling in the pit since the last meeting.

The design for the cabling in the hood has changed slightly with the split in the hood lid now 50/50 rather than 70/30.

HPD Box Systems

It is now foreseen that there will be three systems in the HPD boxes in addition to the main readout. These are:

- Temperature monitors - small pt100 sensors as in the gas in the vessel.    A connector is already included on the patch panel design.

- Light tightness monitors - two small PMTs with different photo-cathodes covering the range of the HPD’s sensitivity. A decision has been made for the type (a Hammamatsu tube) and now a supplier needs to be identified.

- Time alignment laser - a fibre that carries a short laser pulse projecting onto the other HPD box (two fibres per box?). The geometry of this system still needs investigation.

Photon Funnel

During the HPD box/chariot test installation, measurements of the volume for the upper photon funnel were made.    These indicate that due to the tolerance to which the magnetic shield was made and the distortions suffered by the gas enclosure there are a few mm less available than in the ideal model.

This has implications for the Syracuse Magnetic Calibration system.

The CAD model will be remade to take this into account.

It is highly likely that the bottom PF will have a different set of conditions.

Magnetic Distortion Monitoring

A brief email report from Ray Mountain

**********************************

As requested, here is a paragraph summarizing progress with the

RICH-1 mag cal system.

Mechanical:    With the arrival of the driver, all components from

Parker are now in hand.    The next step is to connect them up and

make motion tests.    Then, after that, modifications to the motor

orientation.

Light Source:    The main concern right now is optimizing the optical

design to project the correct spot size from each LED - with little

light leaking from neighboring collimator holes, and enough light

per spot.

**********************************

A meeting will be arranged immediately on Dave Websdale's return from holiday.

The design now has to be an iterative process converging on changes to the PF design and that of the MDM.

Now we have information on the actual space available we will be able to make progress.

Cooling / HPD Mechanics

TS is currently working on the cooling manifolds.

There are different requirements on the data and HV sides of the box as there is shared space between the HV cables and the cooling pipes.

Coolant will be carried along braided SS hose with a PTFE liner. This will give some slight flexibility to allow for tolerances and movement during column extraction.

Off the shelf components are being used in the design.

The flexible lines will be supported by a thin metal sheet.

As we need to make sure the system is dry before a column can be extracted we should be able to drain a column individually.

Examples of the connectors for the patch panels are now available at Imperial College. Some changes to the panels have been mentioned earlier but we are confident of being able to make them.

We have the material for the hood available in the workshop and work can begin as soon as the concept for the cooling system is completed.

The timescale for the completed box will be decided at the meeting on Monday morning.

LAMS

Will Reece (IC PG student) has set up a prototype of the system and made preliminary measurements of a direct and an indirect spot on the CCD camera.

The system seems to be feasible to set up, but delicate.

There have been no major problems encountered yet.

Quartz Windows, Aerogel,        - No change.