Project Management Plan

Project Name: Calice

Version: 0.1

Approval:

|  |  | name | signature | date |  |
| --- | --- | --- | --- | --- | --- |
|  | Project Manager | Rob Halsall | XXXXXXXXX | XXXXXXX |  |
|  | Group Leader | Rob Halsall | XXXXXXXXX | XXXXXXX |  |

Distribution for all updates:

| Project Manager: | Rob Halsall |
| --- | --- |
| Group Leader responsible for the project: | Rob Halsall |
| Division Head responsible for the project: | Steve Quinton |
| Project Managers of related projects: | John Coughlan |
| Programme Manager: | Steve Quinton |
| Quality Manager: | Steve Quinton |

# Management Aspects

## Related Projects

CMS Tracker FED

## Stakeholder Plan

See document calice-shp-v0-1.doc

## Risk Management Plan

See document calice-rmp-v0-1.doc

## Project Staff and Organization

| Name | Institute | Role |
| --- | --- | --- |
| Rob Halsall | RAL | Project Manager CMS Liaison |
| Adam Baird | RAL | Lead Engineer |
| Ed Freeman | RAL | VME & Back End FPGA consultant |
| Ivan Church | RAL | Test/Test Firmware |
| Richard Matson | RAL | Test (JTAG) |
| Chris Day | RAL | DO |
| Bob Thompson | RAL | OM |

| Name | Institute | Role |
| --- | --- | --- |
| Paul Dauncey | IC | Customer/sponsor Software |
| Osman Zorba | IC | Front End FPGA up to FE-BE Interface |
| Dave Mercer | MAN | Back End/VME FPGA Front End FPGA FE-BE Interface |
| Martin Prostranecky | UCL | Trigger FPGA Firmware |
| Matt Warrren | UCL | Trigger FPGA Firmware |

## Training

| Area | Name | Method |
| --- | --- | --- |
| Cadence | Adam Baird | On the job DO assistance |
| Xilinx Virtex II | Ivan Church | CMS Tracker FED |
| CMS Tracker FED | Adam Baird Ivan Church | Rob Halsall assistance CMS Tracker FED Testing |

## Project Plan

See document calice-plan-v0-1.mpp

## Costs and Finance

Total budget estimated at £111K hardware & 20 Staff Months effort.

| Item | Unit Cost | Quantity | Total |
| --- | --- | --- | --- |
| ADC Module | £8090 | 11 | £89K |
| NIM-LVDS Module | £1000 | 1 | £1K |
| Prototype Cables | £100 | 10 | £1000 |
| Final Cables | £70.5 | 64 | £4.5K |
|  |  | Total | £95.5K |

Project Codes are FD31710 CALICE REQUISITIONS and FD31720 CALICE TD STAFF

See document calice-stp-v0-1.xls for estimated Staff To Project profile

See document calice-req-v0-1.xls for estimated requisition costs

## Project Reviews and Documentation

| Review Stage | Date | Documentation |
| --- | --- | --- |
| Conceptual Design | 11-10-2002 | On Web site |
| Preliminary Project | 24-10-2003 | Project Spec Project Management Plan Microsoft Project Plan Staff to Project Spreadsheet |
| Pre-Production Prototype Module | 24-10-2003 | CDR & PPR Documents Schematics & Layout |
| Pre- Production Final Module | 31-04-2004 | CDR & PPR Documents Schematics & Layout Problem Reports Route Cards Test Results from Lab |
| Close Out Review | 31-07-2004 | All available documentation Test Results from Lab Test Results from Cosmics |
| Post Implementation Review | 01-09-2004 | All available documentation Test Results from DESY |

## Project Monitoring and Control

Weekly Project Monitor Forms

## Procurement Plan

RAL OM/DO will procure Readout Boards & Cables

## Software and Equipment

For use at RAL;

| Item | Responsibility | Notes |
| --- | --- | --- |
| Space in R25 Lab | RAL | Exists |
| PC with CAE Tools | RAL | Exists |
| JTAG Test System | RAL | Exists |
| Parallel Cable IV | RAL | Exists |
| XDAQ Software | IC/UCL/MAN | CMS DAQ |
| Test Software | IC/UCL/MAN | Develop |
| VME 64X Crate | IC/UCL/MAN | Exists |
| VME-PCI | IC/UCL/MAN | Exists |

## Quality Plan

The project will be run under the Instrumentation Department Quality System.

Conceptual Design Review held by customer prior to PPRP proposal submission.

## Safety

Standard VME based ADC instrumentation board

Not EMC tested by CCLRC RAL

Make sure system grounding set up correctly

Observe anti static precautions

## Environmental Impact

Not EMC tested by CCLRC RAL

Customer will responsible for disposal at end of life

# Technical Aspects

## Requirements

### See customer documents;

Specification of the readout electronics for the CALICE beam test, Nov 19, 2002

Proposal 317 – CALICE Resubmission, November 12, 2003

## Specification of Deliverables

### Front End Module;

### Back End Section;

See CMS Schematics, PC3025M rev A, 13-11-02

See CMS Firmware & System presentation 05-03-2003

## Manufacturing

Use RAL DO/OM approved PCB manufacturer, Assembly Company and processes.

## Testing and Product Control

The test plan will be a separate document. Product control will be by standard route card for each module with an overall spreadsheet summary.

See documents calice-tp-v0-0.doc, calice-rc-xx.doc, calice-rcs.xls

## Shipping and Installation

Customer will install

Shipping destination TBD – chargeable to project cost center

Modules will be packed in individual anti-static bags and padded foam boxes.

## Maintenance and further orders

This project is part of a technology demonstrator programme and is such is not likely to require long term maintenance.

Review maintenance requirements at the Post Implementation Review